## Sheet1
ID | Task Name | Duration | Start | Finish | Predecessors | Resource Names | % Complete | Notes
1
2 | DESIGN, PLAN | 42 days | 2014-01-31 | 2014-03-31 |  |  | 0%
3 | Hold project kickoff meeting | 1 day | 2014-01-31 | 2014-01-31 |  |  | 0%
4 | Build risk and issue tracking system | 1 day | 2014-01-31 | 2014-01-31 | 3SS |  | 0%
5 | Develop Notes to O365 migration strategy | 5 days | 2014-02-03 | 2014-02-07 | 3 |  | 0%
6 | Identify the email coexistence strategy | 1 day | 2014-02-06 | 2014-02-06 | 3FS+3 days |  | 0%
7 | Document all namespaces and domain names moving forward - UPN, SIP domain | 5 days | 2014-02-10 | 2014-02-14 | 6FS+1 day |  | 0%
8 | Document forwarding namespace for Notes to Mimecast for migrated users | 5 days | 2014-02-10 | 2014-02-14 | 7SS |  | 0%
9 | Plan DNS entries for O365 | 15 days | 2014-02-10 | 2014-02-28 | 7SS |  | 0%
10 | Plan DNS entries for Lync, Exchange & ADFS - Autodiscover, Outlook Anywhere, Federation | 15 days | 2014-02-10 | 2014-02-28 | 7SS |  | 0%
11 | Document all DNS entries and URL's | 3 days | 2014-02-13 | 2014-02-17 | 9SS,10SS |  | 0%
12 | Identify mailbox size and item counts | 1 day | 2014-02-05 | 2014-02-05 | 3FS+2 days |  | 0%
13 | Plan for mail-enabled applications | 1 day | 2014-02-05 | 2014-02-05 | 12SS |  | 0%
14 | Plan & Document for user identity and account provisioning | 17 days | 2014-02-10 | 2014-03-04 | 7SS |  | 0%
15 | Identify Active Directory preparation and remediation requirements | 5 days | 2014-02-10 | 2014-02-14 | 14SS |  | 0%
16 | Identify current network links, user concentration, and current utilization | 9 days | 2014-02-04 | 2014-02-14 | 3FS+1 day |  | 0%
17 | Identify versions of Exchange infrastructure and service packs | 1 day | 2014-02-06 | 2014-02-06 | 6SS |  | 0%
18 | Identify on-premises infrastructure server requirements for O365 compatibility | 5 days | 2014-02-06 | 2014-02-12 | 6SS |  | 0%
19 | Identify the operating systems and client applications | 1 day | 2014-02-05 | 2014-02-05 | 3FS+2 days |  | 0%
20 | Identify the mobile platform that your organization will use | 1 day | 2014-02-05 | 2014-02-05 | 19SS |  | 0%
21 | Document BYOD policy | 3 days | 2014-02-05 | 2014-02-07 | 19SS |  | 0%
22 | Document Activesync policies | 6 days | 2014-02-05 | 2014-02-12 | 19SS |  | 0%
23 | Develop an end user and administrator training schedule and delivery mechanism | 21 days | 2014-02-10 | 2014-03-10 | 3FS+5 days |  | 0%
24 | Schedule Local IT / end user training | 15 days | 2014-03-11 | 2014-03-31 | 23 |  | 0%
25 | Define user migrations in batches and document VIPs, managers and associated admins | 15 days | 2014-02-17 | 2014-03-07 | 5FS+5 days |  | 0%
26 | Develop end-user communications strategy | 10 days | 2014-02-10 | 2014-02-21 | 3FS+5 days |  | 0%
27 | Review operations guidelines | 25 days | 2014-02-24 | 2014-03-28 | 3FS+15 days |  | 0%
28 | Executive Agenda Overview - handled by Pgm Mgr and Sponsors | 1 day | 2014-03-10 | 2014-03-10 |  |  | 0%
29 | Communicate plans to team and get sign off from sponsor - handled with deliverables | 1 day | 2014-03-11 | 2014-03-11 | 28 |  | 0%
30 | Milestone: Architecture Designed | 0 days | 2014-02-24 | 2014-02-24 | 8,11,17,18 |  | 0%
31 | Milestone: AD Planned | 0 days | 2014-02-21 | 2014-02-21 | 15 |  | 0%
32 | Milestone: Network Planned | 0 days | 2014-02-14 | 2014-02-14 | 16 |  | 0%
33 | Milestone: Domains Documented | 0 days | 2014-02-28 | 2014-02-28 | 25FS-6 days |  | 0%
34 | Milestone: Migration, Software and Phone Rollout Planned | 0 days | 2014-03-07 | 2014-03-07 | 22,25,26 |  | 0%
35 | Milestone: Training Scheduled | 0 days | 2014-03-31 | 2014-03-31 | 24 |  | 0%
36
37 | CONFIGURE | 74 days | 2014-02-06 | 2014-05-20 |  |  | 0%
38 | Identify desktop OS versions and service packs globally | 45 days | 2014-03-17 | 2014-05-16 | 19FS+27 days |  | 0%
39 | Identify browser versions globally | 45 days | 2014-03-17 | 2014-05-16 | 38SS |  | 0%
40 | Ingredients Firewall Changes for Mimecast mailbox sync | 5 days | 2014-02-10 | 2014-02-14 | 3FS+5 days |  | 0%
44 | Define temporary migration domain & create MX records for routing at Mimecast | 3 days | 2014-02-10 | 2014-02-12 | 40SS |  | 0%
46 | Setup forest level trusts | 1 day | 2014-02-14 | 2014-02-14 | 45FF |  | 0%
47 | Purchase / Add O365 licenses | 25 days | 2014-02-10 | 2014-03-14 | 40SS |  | 0%
48 | Enable O365 tenant | 15 days | 2014-02-10 | 2014-02-28 | 47SS |  | 0%
49 | Add Global O365 admins | 1 day | 2014-03-03 | 2014-03-03 | 48 |  | 0%
50 | Add hosted domains in Office 365 | 1 day | 2014-03-18 | 2014-03-18 | 48 |  | 0%
51 | Verify O365 hosted domains | 1 day | 2014-03-03 | 2014-03-03 | 48 |  | 0%
52 | Analyze AD objects for issues | 31 days | 2014-02-06 | 2014-03-20 | 3FS+3 days |  | 0%
53 | Clean up AD user objects - unsupported length and characters | 14 days | 2014-02-10 | 2014-02-27 | 52SS+2 days |  | 0%
54 | Update all users with correct UPN - part of clean up activities | 14 days | 2014-02-10 | 2014-02-27 | 52SS+2 days |  | 0%
55 | Extend AD schema for Exchange - forestprep & domainprep | 1 day | 2014-02-14 | 2014-02-14 | 15FS-1 day |  | 0%
56 | Setup new on-premise Exchange Environment | 20 days | 2014-02-18 | 2014-03-17 | 7SS+6 days |  | 0%
57 | Buy, Mint, Install certificates for on-premise & online Exchange | 5 days | 2014-03-18 | 2014-03-24 | 56 |  | 0%
59 | ADFS Logical design | 1 day | 2014-03-03 | 2014-03-03 | 54FS+1 day |  | 0%
60 | Identify ADFS IP addresses, ports, virtual IPs for HW loadbalancer for network changes | 2 days | 2014-03-04 | 2014-03-05 | 59 |  | 0%
61 | Audit ADFS servers and check for any required service packs | 1 day | 2014-03-06 | 2014-03-06 | 60 |  | 0%
62 | Submit change requests for ADFS service pack updates and network updates | 1 day | 2014-03-07 | 2014-03-07 | 61 |  | 0%
63 | Complete ADFS service pack updates | 1 day | 2014-03-13 | 2014-03-13 | 62FS+3 days |  | 0%
64 | ADFS changes to firewalls and NAT | 1 day | 2014-04-04 | 2014-04-04 | 63FS+15 days |  | 0%
65 | Install second ADFS server and ADFS proxy servers (Dii side) | 3 days | 2014-03-17 | 2014-03-19 | 63FS+1 day |  | 0%
66 | Setup O365 Exchange Online/Skype Online | 1 day | 2014-03-20 | 2014-03-20 | 65 |  | 0%
67 | Skype SIP domain - define valid SIP domains based on logon UPN | 1 day | 2014-03-20 | 2014-03-20 | 65 |  | 0%
68 | Client connectivity firewall port changes from Internal to O365 | 5 days | 2014-03-21 | 2014-03-27 | 66 |  | 0%
69 | Infrastructure firewall port changes from internal & DMZ to O365 | 5 days | 2014-03-21 | 2014-03-27 | 66 |  | 0%
70 | Configure ADFS for SSO with Azure AD | 3 days | 2014-03-20 | 2014-03-24 | 65 |  | 0%
71 | Enable single sign-on (identity federation) | 3 days | 2014-03-20 | 2014-03-24 | 70SS |  | 0%
72 | Prepare your on-premises Active Directory for directory synchronization to Azure | 22 days | 2014-02-20 | 2014-03-21 | 52SS+10 days |  | 0%
73 | Install the Directory Synchronization Tool and perform synchronization | 22 days | 2014-02-20 | 2014-03-21 | 52SS+10 days |  | 0%
74 | Validate Dir Sync | 1 day | 2014-03-24 | 2014-03-24 | 73 |  | 0%
75 | Resolve open DirSync issues | 2 days | 2014-03-25 | 2014-03-26 | 74 |  | 0%
76 | Buy, Mint, Install certificates for Exchange, Skype for O365 | 2 days | 2014-03-27 | 2014-03-28 | 75 |  | 0%
77 | Configure O365 Exchange - Connectors, mail flow, mobile | 3 days | 2014-03-31 | 2014-04-02 | 47,76 |  | 0%
78 | Configure O365 webservices for Exchange hybrid | 2 days | 2014-04-02 | 2014-04-03 | 77FS-1 day |  | 0%
79 | Run hybrid configuration wizard for Exchange hybrid | 3 days | 2014-04-04 | 2014-04-08 | 78 |  | 0%
80 | Testing Outlook, F/B and Mail Flow | 7 days | 2014-04-01 | 2014-04-09 |  |  | 0%
81 | Test Outlook Autodiscover in hybrid with existing config | 5 days | 2014-04-01 | 2014-04-07 | 56,79FS-6 days |  | 0%
82 | Test Outlook Anywhere in hybrid with existing config | 5 days | 2014-04-01 | 2014-04-07 | 56,79FS-6 days |  | 0%
83 | Change configure of Outlook Anywhere/Autodiscover if necessary | 2 days | 2014-04-04 | 2014-04-07 | 81FF,82FF |  | 0%
84 | Test free/busy between hybrid exchange environments | 3 days | 2014-04-07 | 2014-04-09 | 83FS-1 day |  | 0%
85 | Test mailflow between hybrid exchange environments | 3 days | 2014-04-07 | 2014-04-09 | 84SS |  | 0%
86 | Test mailflow to Internet in hybrid exchange environments | 3 days | 2014-04-07 | 2014-04-09 | 84SS |  | 0%
88 | Testing Admin and Functional | 7 days | 2014-04-08 | 2014-04-16 |  |  | 0%
89 | Create administrative and functional test scripts | 2 days | 2014-04-08 | 2014-04-09 | 82 |  | 0%
90 | Validate administrative and functional test scripts | 2 days | 2014-04-10 | 2014-04-11 | 89 |  | 0%
91 | Test and validate email migration and coexistence | 3 days | 2014-04-14 | 2014-04-16 | 84,85,86,90 |  | 0%
92 | Configure Skype and enable all users with SIP URI | 1 day | 2014-04-18 | 2014-04-18 |  |  | 0%
93 | Deploy client applications and the Office 365 desktop setup globally to all end users | 46 days | 2014-03-17 | 2014-05-19 | 25 |  | 0%
94 | location1 software deployment | 4 days | 2014-03-17 | 2014-03-20 | 116SS-8 days |  | 0%
95 | location2 software deployment | 16 days | 2014-03-24 | 2014-04-14 |  |  | 0%
101 | Prepare customer service desk | 12 days | 2014-03-17 | 2014-04-01 | 94SS |  | 0%
102 | Update migration batches as needed | 27 days | 2014-04-14 | 2014-05-20 |  |  | 0%
103 | Develop Operations guidelines | 15 days | 2014-03-31 | 2014-04-18 | 27 |  | 0%
104 | Communicate Development completed tasks to team and sponsors - Covered in meetings | 1 day | 2014-04-21 | 2014-04-21 | 103 |  | 0%
106 | Milestone: Office 365 Online | 0 days | 2014-03-20 | 2014-03-20 | 51,66,67 |  | 0%
107 | Milestone: AD and AD Sync Completed | 0 days | 2014-03-24 | 2014-03-24 | 71 |  | 0%
108 | Milestone: Workstations Configured | 0 days | 2014-05-19 | 2014-05-19 | 93 |  | 0%
109
110 | IMPLEMENTATION, MIGRATION | 67 days | 2014-03-10 | 2014-06-10 |  |  | 0%
111 | Send out initial communications to users with dates - one mon, three wks, one wk | 54.6 days | 2014-03-21 | 2014-06-05 |  |  | 0%
112 | Pre-announcements to Key-users and Local IT contacts | 37 days | 2014-03-21 | 2014-05-19 | 128SS-21 days |  | 0%
113 | Pre-announcement to Notes users | 37 days | 2014-03-31 | 2014-05-27 | 128SS-15 days |  | 0%
115 | Reminder migration date and Instructions on first use sent to users | 34 days | 2014-04-14 | 2014-06-05 | 128SS-5 days |  | 0%
116 | Migration from Notes to Exchange, 30 days mail, calendar, contacts | 7 days | 2014-03-27 | 2014-04-04 |  |  | 0%
117 | Assign licenses to users in O365 | 27 days | 2014-04-28 | 2014-06-04 | 128SS-5 days |  | 0%
118 | Sync mailbox data to Mimecast | 20 days | 2014-03-10 | 2014-04-04 | 51FS+4 days |  | 0%
119 | Mailbox-enable all Ingredients users in O365 Exchange and change targetaddress to point to Notes address (prep) | 28 days | 2014-04-28 | 2014-06-04 | 128SS-5 days |  | 0%
120 | Change DNS records for Exchange O365 | 2 days | 2014-04-14 | 2014-04-15 | 90 |  | 0%
121 | Change Internal and External Skype DNS entries to point to O365 | 2 days | 2014-04-16 | 2014-04-17 | 120 |  | 0%
122 | Enable/Configure Exchange Activesync policies per BYOD policies per user or group | 2 days | 2014-04-16 | 2014-04-17 | 120 |  | 0%
123 | Reminder migration and Instructions for Mobile configuration sent to users | 25 days | 2014-05-02 | 2014-06-05 | 128SS-1 day |  | 0%
124 | Order new devices/adjust plans to allow data (BB users) | 35 days | 2014-03-10 | 2014-04-25 | 34 |  | 0%
125 | Configure mobile phones and devices for Office 365 | 36 days | 2014-04-18 | 2014-06-06 | 124FS-6 days |  | 0%
126 | Change SMTP address and addressbooks for multi-functionals | 25 days | 2014-05-05 | 2014-06-06 | 128SS |  | 0%
127 | Migrate calendar & contacts to O365 Exchange mailboxes (Quest migration) | 25 days | 2014-05-05 | 2014-06-06 |  |  | 0%
128 | Location1 migration from Notes to O365 (M1) | 1 day | 2014-05-05 | 2014-05-05 |  |  | 0%
129 | Location2 migration from Notes to O365 (M2) | 12 days | 2014-05-05 | 2014-05-20 | 128SS |  | 0%
138 | Move users from Exchange to O365 | 2 days | 2014-06-09 | 2014-06-10 | 137 |  | 0%
139 | Modify Notes person doc to be other internet person | 27 days | 2014-05-05 | 2014-06-10 | 128SS |  | 0%
140 | Remove "targetaddress" from migrated user account to accept inbound email | 26 days | 2014-05-05 | 2014-06-10 | 128SS |  | 0%
141 | Collect mobile devices | 23 days | 2014-05-09 | 2014-06-10 | 128FS+3 days |  | 0%
142 | Milestone: Sync Mailboxes | 0 days | 2014-04-01 | 2014-04-01 | 118FS-4 days |  | 0%
143 | Milestone: Location1 Migrated | 0 days | 2014-04-04 | 2014-04-04 | 116 |  | 0%
144 | Change DNS records for Exchange O365 - after migrations are completed | 2 days | 2014-05-28 | 2014-05-29 | 137 |  | 0%
145 | Milestone: Location2 Migrated | 0 days | 2014-05-05 | 2014-05-05 | 128 |  | 0%
153 | Milestone: Phone Migration Complete | 0 days | 2014-06-10 | 2014-06-10 | 141 |  | 0%
154
155 | HYPERCARE, STABILIZATION | 62 days | 2014-03-27 | 2014-06-20 |  |  | 0%
156 | Perform post-migration service testing | 10 days | 2014-06-09 | 2014-06-20 | 136 |  | 0%
157 | Welcome message and FAQs sent to users | 52 days | 2014-03-27 | 2014-06-06 | 116SS |  | 0%
158 | Coordination to direct multi-functional devices to the new mail servers | 25 days | 2014-05-06 | 2014-06-09 | 145 |  | 0%
159 | Hypercare | 60 days | 2014-03-31 | 2014-06-20 | 143FS-5 days |  | 0%
160 | Milestone: User Training and Hypercare Ends | 0 days | 2014-06-20 | 2014-06-20 | 159FF |  | 0%
161
162 | PM Support | 106 days | 2014-01-31 | 2014-06-27 |  |  | 0%
163 | Project Management - initiation, planning and execution | 100 days | 2014-01-31 | 2014-06-20 |  |  | 0%
164 | Project Close | 5 days | 2014-06-23 | 2014-06-27 | 163 |  | 0%